## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | Inspect |  |  |  |  | Project Name: | Inspect
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
| Open | High | Low | Yellow | EXAMPLE: Current project skill set may not be adequate to complete all project work. The current development team has been working in a Windows 2k environment, and the current requirements are for a LINUX environment. The project schedule would require 1500 development hours of a skilled LINUX operator, and approximately 1900 to 2200 if we retrain our current resources. | EXAMPLE: If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | EXAMPLE: Schedule approaches the required start date with no identification of required skill sets. | EXAMPLE: Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | EXAMPLE: Find internal resource that meets required skill set or train existing resources on LINUX. | EXAMPLE: Find resource that meets required skill set through external hiring sources.
1 | Open | High | Medium | Red | The team currently lack experience with the choosen development environment, Android Studio. This will be the IDE of choice for creating the inspection app. | Lack of experience with Android Studio will greatly hinder the progress within the team, as team member may struggle or be left unable to complete tasks in the devlopment environment. | Overall Project Failure | Team member struggling to complete task due to lack of knowledge within the environment | Lack of progress on some or all aspects of the devlopment project | Mitigation | Team members to extend their knowledge and familarity with android studio through the used of tutorials. | If the response strategy proves to be insufficient, external sources such as experts/friends/tutors familiar or currently working with Android Studio are to be consulted to bridge the knowledge gap.
2 | Open | Low | High | Yellow | External pressure on team members such as scheduling conflicts, deadlines for other subjects and student life in general could affect the ability for individuals to contribute to tasks. | Could lead to individuals becoming behind on their work and affect deadlines associated with parts of this project. | Schedule | Team member struggling to meet the deadlines set within an iteration | Work not being completed within deadlines due to team member feeling overwhelmed from external factors | Acceptance | Accept that this will occur through the project and can't be completely eliminated. | Where possible alter schedule if it is impacted negatively.
3 | Open | Medium | Medium | Yellow | Getting stuck on a bug or implementing a feature | Will affect project deadlines and ability of the group to complete tasks in a timely maner | Schedule | Deadlines may not be completed on time delaying areas of the project | Expected time for an item to be fixed is taking longer than assigned with no reasoning | Avoidance | Avoid an issue like this causing massive impact by making sure invididuals voice when they're struggling, so the rest of the group can help earlier rather than later. | If the issue is brought forth at a later time, team members will have to temporarily shift their focus from their own assigned tasks to assist the individual in need, and the individual himself will need to consult external sources, either through tutorials, forums, or friends with the proper technical expertise.
4 | Open | Medium | Medium | Yellow | Comprismising on functionality due to time constraints in order to have a functional product | Product may not contain all the feature that was originally promised or intended. | Feasibility | Parts of the project falling behind due to difficults faced implementing ideas | Unsuspected issues causing delays on elements being completed on time | Avoidance | Avoid this from occuring by keeping goals realisitic and not over commiting on functionality | The functionality may need to be redesigned or streamlined if goals are unrealistic.
5 | Open | High | Low | Yellow | Poor planning causing priorities to not be ordered correctly. Meaning items that are actually of high priority being labelled as lower priority. Therefore they are not given the proper attention required | The overall quality and functionality of the final product could be hindered | Project Management | Tasks that were meant to be completed quickly are taking longer than needed due to unforseen extra tasks required to complete the task or the quality of the compeleted task isn't what was expected | Tasks taking longer than expected delaying the project or not being completed to the quality expected in the required time | Avoidance | Re-evaluating items if they are taking longer than required to see if they need more importance placed on them than originally planned. Also see if more time is required to ensure a high quality standard is met. | Items which are taking longer than expected may need to be simplified/streamlined to avoid impacting other work items in the schedule.
6 | Open | Medium | Low | Green | Failure to complete a low priority task in required time | Could affect other parts of the project so the impact could be greater, delaying other parts of the project relying on this task | Schedule | Absence of required task being submitted, causing functionality to be broken | Absence of required task being submitted | Avoidance | Ensure members notify group early about any issues completing their tasks on time so it can be managed and avoided. | If the issue is brought forth at a later time, team members will have to temporarily shift their focus from their own assigned tasks to assist the individual in need, and the individual himself will need to consult external sources, either through tutorials, forums, or friends with the proper technical expertise. The low-priority task may need to be simplified or discarded entirely if is isn't doable by the due date.
7 | Open | High | Low | Yellow | Failure to complete a high priority task in the required time | Would have great impact on the project as a whole, including reduced functionality or no functionality | Schedule | Absence of required task being submitted, causing functionality to be broken | Absence of required task being submitted | Avoidance | Ensure members notify group early about any issues completing their tasks on time so it can be managed and avoided. | If the issue is brought forth at a later time, team members will have to temporarily shift their focus from their own assigned tasks to assist the individual in need, and the individual himself will need to consult external sources, either through tutorials, forums, or friends with the proper technical expertise. The high-priority task may also need to be simplified if it is unable to be completed by the due date.
8 | Open | Medium | Low | Green | Communication break down including poor ocmmunicaiton, failured to ahere protocols set out in the team charter. | Delays caused as people may be waiting on communication to move forward with their tasks | Schedule | Unanswer communication being repeated to attempt to get answers | Absence of communication from a team member | Avoidance | Team charter clearly states to let others known if you unable to communication for any reason. Also it is expected you will communicate frequently. | If the team member remains non-responsive, the communication protocol strike system should be enforced and the team member made aware of this to encourage frequent communication.
9 | Open | Medium | Low | Green | Data loss due to hardware failure, software failure or human error | Delays redoing work | Data/Information | Work completed not being saved or visible | Human error, sudden hardware or software issues | Avoidance | Data should be backed up online, with code via git and documents via google drive to avoid this problem | Employment of data recovery software.
10 | Open | High | Medium | Red | Modules, libraries etc being difficult to learn and implement | If this libraries or modules are needed to ensure the projects success the impact could lead to reduced functionality or complete project failure | Overall Project Failure | Work requiring modules or libraries not functioning | Tasks not being compeleted due to difficult integrating required modules, libraries etc. | Mitigation | Test how to use these modules, libraries etc early on to reduce the risk later in the project, if need be changing requirements to suit. | Use alternative library or drop feature
11 | Open | Low | Low | Green | Failing to meet report issues or information in full in a timely manner | Could lead to miscommunication and the overlap of work that was not logged properly | Schedule | Task that weren't reported on being completed by multiple member or incorrectly due to lack of information from all parties | Work overlapping, task being done more than once by different people | Avoidance | Ensure all members communiate in a timely maner with accordance to team charter | Allocate a portion of time each week to review the documentation/reporting, ensuring each member is up to date and correctly filling out the approrpriate sections.
| Open | Low | Low | Green | Scope creep inflates scope | Uncontrolled changes and continuous growth of scope such as but not limited to contributors adding their own product features that aren't in requirements. | Schedule | Unnecessary features added that arent assigned or within scope orf project or assigned tasks | Tasks taking too long, features just "appearing" | Avoidance | Clear communication to ensure team members are focused on their assigned tasks | Remove extra added features to minimze time spent maintaining code, debugging, bugfixing etc.
| Open | High | Medium | Red | Scope estimates are inaccurate | Scope of a task or features requirements grossly underestimated | Schedule | A task not progressing as quicly as forecast or runs over time budget allocated | Task has more hours logged than assigned in iteration plan | Mitigation | Team members are to communicate scope issue in assigned tasks as soon as possible | Task will be re evaluated upon being flagged

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources